## Legend
CAREER CONNECT (JOBB) - AUTH MODULE TEST CASES
START HERE — THIS WORKBOOK CONTAINS 6 WORKSHEETS
Use the sheet tabs at the bottom to review: Summary, Legend, Signup, OTP Verification, Login and Defects.
APPROACH | What was done
Method | Black box functional testing through the user interface. The application was run locally and each case was executed by hand on the Signup and OTP screens.
Expected results | No formal requirement document was available. Expected results are clearly stated testing assumptions based on common validation and security practices, then compared with the running application.
Scope | Registration, email verification and the related unverified-login check. Job posting, applications and API-level testing are outside this workbook.
STATUS | What it means
Pass | The actual result matched the expected result.
Fail | The actual result did not match. A defect is recorded in the Remarks column.
Not Executed | The case is designed but has not been run yet.
Blocked | The case could not be run because something else prevented it.
COLUMN | What goes in it
Precondition | What must already be true before the steps are followed.
Test Steps | Numbered steps. Another tester should be able to execute the case from these alone.
Test Data | The exact input used, with personal information masked before sharing.
Expected Result | What should happen according to the rules the application enforces.
Actual Result | What actually happened, including the exact message shown on screen.
Severity | Filled in only when a case fails.
Technique | Positive, Negative, Equivalence Partitioning, Boundary Value Analysis, Security or Data verification.
SHEETS | What each one holds
Signup | 28 cases covering registration fields, phone and password boundaries, duplicate submission and email rules.
OTP Verification | 15 cases covering verification, expiry, resend, reuse, input validation and resend controls.
Defects | The 10 defects found, including severity, observed behaviour and business/security impact.
Summary | Counts by status, the defect list and the single most important finding.
Login | 15 designed cases covering credentials, required fields, normalization, unverified accounts, repeated attempts and common security inputs.
SEVERITY | How it was judged
High | A security weakness, or a failure that stops users completing a core task.
Medium | Wrong behaviour that reaches the database or blocks a valid user, with a workaround available.
Low | Wording, layout or polish. No functional impact.

## Signup
TEST CASES - USER REGISTRATION (Signup screen)
Project : Career Connect (JOB PORTAL)
Test Case ID | Module | Test Scenario | Precondition | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Technique | Remarks
TC_REG_001 | Signup | Register with all valid details | Signup page is open and the email is not already registered | 1. Open the Signup page 2. Fill Full Name, Email, Phone Number, Password and Confirm Password 3. Select a role 4. Click Signup | joshiaavash111@gmail.com / 98******52 / Pa$$@1234 / Pa$$@1234 / Jobseeker | Account is created and the OTP verification screen opens | Account was created and the OTP screen opened as expected | Pass |  | Positive
TC_REG_002 | Signup | Submit with Full Name empty | Signup page is open | 1. Leave Full Name blank 2. Fill every other field correctly 3. Select a role 4. Click Signup | fullname blank, all other fields valid | A validation message naming the Full Name field | Message displayed: Please enter your full name | Pass |  | Negative
TC_REG_003 | Signup | Submit with Email empty | Signup page is open | 1. Leave Email blank 2. Fill every other field correctly 3. Click Signup | email blank, all other fields valid | A validation message naming the Email field | Message displayed: Please enter your email | Pass |  | Negative
TC_REG_004 | Signup | Submit with Phone Number empty | Signup page is open | 1. Leave Phone Number blank 2. Fill every other field correctly 3. Click Signup | phoneNumber blank, all other fields valid | A validation message naming the Phone Number field | Message displayed: Please enter your phone number | Pass |  | Negative
TC_REG_005 | Signup | Submit with Password empty | Signup page is open | 1. Leave Password blank 2. Fill every other field correctly 3. Click Signup | password blank, all other fields valid | A validation message naming the Password field | Message displayed: Please enter the password | Pass |  | Negative
TC_REG_006 | Signup | Submit without selecting a role | Signup page is open | 1. Fill every field correctly 2. Do not select Jobseeker or Recruiter 3. Click Signup | role not selected | A validation message asking the user to select a role | Message displayed: Please select the role | Pass |  | Negative
TC_REG_007 | Signup | Full Name containing digits | Signup page is open | 1. Enter Aavash123 in Full Name 2. Fill every other field correctly 3. Select a role 4. Click Signup 5. Check whether the account was created | fullname Aavash123 | Rejected with a message that a name must not contain numbers | Registration completed successfully. Aavash123 was accepted as a valid name and the account was created | Fail | Medium | Negative | Full Name accepts digits. Logged as D-01.
TC_REG_008 | Signup | Phone number not starting with 98 | Signup page is open | 1. Enter 1234567890 in Phone Number 2. Fill every other field correctly 3. Click Signup | phoneNumber 1234567890 | Rejected with a message about the phone number prefix | Message displayed: Phone number must start with 98 | Pass |  | Negative / EP
TC_REG_009 | Signup | Phone number shorter than 10 digits | Signup page is open | 1. Enter 987 in Phone Number 2. Fill every other field correctly 3. Click Signup | phoneNumber 987 | Rejected with a message about the required length | Message displayed: Phone number must be 10 digits | Pass |  | BVA (below min)
TC_REG_010 | Signup | Password shorter than the minimum length | Signup page is open | 1. Enter Pas@1 in Password and Confirm Password 2. Fill every other field correctly 3. Click Signup | password Pas@1 in both fields | Registration is rejected with a message explaining the minimum password length | Message displayed: Password must be at lease 6 digits with at least one special character , one capital letter and must be one number. | Pass |  | Negative | The password rule works, but the message has spelling and wording errors. Logged as D-02.
TC_REG_011 | Signup | Password and Confirm Password do not match | Signup page is open | 1. Enter Pass@1234 in Password 2. Enter Pass@4321 in Confirm Password 3. Fill every other field correctly 4. Click Signup | Pass@1234 and Pass@4321 | Rejected with a mismatch message | Message displayed: Password and confirm password did not match | Pass |  | Negative
TC_REG_012 | Signup | Register with an email that is already registered | An account already exists with the email used | 1. Fill the form using an already registered email 2. Fill every other field correctly 3. Click Signup | an existing email address | Rejected with a message that the email is already registered | Message displayed: Mail is registered previously | Pass |  | Negative
TC_REG_013 | Signup | Phone number starting with 97 | Signup page is open | 1. Enter 9741234567 in Phone Number 2. Fill every other field correctly 3. Click Signup | phoneNumber 9741234567 | Accepted, because 97 is a valid Nepali mobile prefix | Message displayed: Phone number must start with 98 | Fail | Medium | EP / Negative | A valid Nepali mobile number beginning with 97 is rejected. Logged as D-03.
TC_REG_014 | Signup | Phone number longer than 10 digits | Signup page is open | 1. Enter 98123456789 in Phone Number 2. Fill every other field correctly 3. Click Signup | phoneNumber 98123456789 | Either the field stops at 10 digits or a length message is shown | Message displayed : Phone number must be 10 digits . | Pass |  | BVA (above max)
TC_REG_015 | Signup | Phone number of exactly 10 digits | Signup page is open | 1. Enter 9812345678 in Phone Number 2. Fill every other field correctly 3. Click Signup | phoneNumber 9812345678 | Accepted and registration proceeds | Account was created and the OTP screen opened as expected | Pass |  | BVA (valid)
TC_REG_016 | Signup | Letters entered in the Phone Number field | Signup page is open | 1. Type abcdefghij in Phone Number 2. Fill every other field correctly 3. Click Signup | phoneNumber abcdefghij | Letters are not accepted, or a validation message is shown | Message displayed: Phone number must start with 98 | Pass |  | Negative | The input is rejected, but the prefix message does not explain that letters are invalid. Consider logging a separate message-quality defect.
TC_REG_017 | Signup | Email in an invalid format | Signup page is open | 1. Enter aavash@ in Email 2. Fill every other field correctly 3. Click Signup | email aavash@ | Rejected with an invalid email message | Message Displayed : Email must end with @gmail.com | Pass |  | Negative
TC_REG_018 | Signup | Full Name containing unsupported symbols | Signup page is open | 1. Enter aavash@#$ in Full Name 2. Fill every other field correctly 3. Click Signup | fullname aavash@#$ | Registration is rejected for unsupported name symbols | Registration completed successfully. aavash@#$ was accepted as a valid name and the account was created | Fail | Medium | Negative | Full Name accepts unsupported symbols. Logged as D-04.
TC_REG_019 | Signup | Leading and trailing spaces in the email | Signup page is open | 1. Enter the email with a space before and after 2. Fill every other field correctly 3. Click Signup | ' joshiaavash111@gmail.com ' | Spaces are trimmed and registration succeeds | Account was created and the OTP screen opened as expected | Pass |  | Negative / EP
TC_REG_020 | Signup | Password field masks the input | Signup page is open | 1. Type a password in the Password field 2. Observe the characters shown | Pass@1234 | Characters are shown as dots, never as plain text | Result : Characters are not shown | Pass |  | Security / UI
TC_REG_021 | Signup | Same email registered in a different letter case | An account already exists with joshiaavash111@gmail.com | 1. Register using JOSHIAAVASH111@GMAIL.COM 2. Fill every other field correctly 3. Click Signup | JOSHIAAVASH111@GMAIL.COM | Treated as the same email and rejected as a duplicate | Message Displayed : Email is already used | Pass |  | Negative / EP | If this creates a second account, one person can hold two accounts on the same address
TC_REG_022 | Signup | Double click on the Signup button | The form is filled correctly | 1. Fill the form correctly 2. Double click Signup quickly 3. Check how many accounts were created | valid registration data | Only one account is created | Result : Account created only once | Pass |  | Negative / Data
TC_REG_023 | Signup | Submit with Confirm Password empty | Signup page is open | 1. Fill every field correctly 2. Leave Confirm Password blank 3. Select a role 4. Click Signup | confirmPassword blank | Registration is rejected with a message naming Confirm Password | Result: Please enter confirm Password | Pass |  | Negative
TC_REG_024 | Signup | Password at the minimum valid length | Signup page is open | 1. Enter a password containing exactly the stated minimum number of characters 2. Meet all character rules 3. Complete and submit the form | Ab@123 | Registration proceeds when all password rules are satisfied | Message displayed: Password must be at lease 6 digits with at least one special character , one capital letter and must be one number. | Fail | Medium | BVA (valid minimum) | A password meeting the shown rules is rejected. Logged as D-05.
TC_REG_025 | Signup | Password without an uppercase letter | Signup page is open | 1. Enter test@123 in Password and Confirm Password 2. Complete and submit the form | test@123 | Registration is rejected with a message requiring an uppercase letter | Account was created and the OTP screen opened as expected | Fail | Medium | Negative / EP | A password without an uppercase letter is accepted. Logged as D-06.
TC_REG_026 | Signup | Password without a number | Signup page is open | 1. Enter Test@abc in Password and Confirm Password 2. Complete and submit the form | Test@abc | Registration is rejected with a message requiring a number | Message displayed: Password must be at lease 6 digits with at least one special character , one capital letter and must be one number. | Pass |  | Negative / EP
TC_REG_027 | Signup | Password without a special character | Signup page is open | 1. Enter Test1234 in Password and Confirm Password 2. Complete and submit the form | Test1234 | Registration is rejected with a message requiring a special character | Message displayed: Password must be at lease 6 digits with at least one special character , one capital letter and must be one number. | Pass |  | Negative / EP
TC_REG_028 | Signup | Register with a valid non-Gmail email | Signup page is open and the email is not registered | 1. Enter a valid non-Gmail email 2. Fill every other field correctly 3. Select a role 4. Click Signup | joshiaavash@outlook.com | Registration succeeds because Outlook is a valid email provider | Message Displayed : Email must end with @gmail.com | Fail | Medium | Positive / EP | A valid Outlook address is rejected because it is not Gmail. Logged as D-07.

## OTP Verification
TEST CASES - EMAIL OTP VERIFICATION
Test Case ID | Module | Test Scenario | Precondition | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Technique | Remarks
TC_OTP_001 | OTP | Verify with the correct OTP | Registration is complete and the OTP email has arrived | 1. Open the email and read the code 2. Enter the code on the OTP screen 3. Submit | 6-digit code received by the dedicated test account | The email is verified and the user reaches their account | Message displayed: OTP is correct, signing in. The login options appears | Pass |  | Positive
TC_OTP_002 | OTP | Verify with a wrong OTP | The OTP screen is open | 1. Enter a code that does not match 2. Submit 3. Observe whether the account opens | an incorrect 6 digit code | Verification fails and the account does not open | Verification was rejected with a wrong OTP message and the account did not open | Pass |  | Negative
TC_OTP_003 | OTP | Submit with the OTP field empty | The OTP screen is open | 1. Leave the OTP field blank 2. Submit | otp blank | A validation message asking for the OTP | Message displayed: please Enter the OTP | Pass |  | Negative
TC_OTP_004 | OTP | Verify after the OTP has expired | An OTP was generated more than the validity period ago | 1. Register and note the time 2. Wait past the stated expiry 3. Enter the correct code and submit | the correct code after expiry | Rejected with an expiry message | Message displayed: OTP is expired click to resent it | Pass |  | BVA (time) | Check the email text for the stated validity period and test just before and just after it
TC_OTP_005 | OTP | Reuse an OTP that was already used | The OTP was verified successfully once | 1. Verify once successfully 2. Log out 3. Try the same code again | the same code twice | The second attempt is rejected | Message displayed: Wrong OTP | Pass |  | Negative / Security
TC_OTP_006 | OTP | Repeated wrong OTP attempts | The OTP screen is open | 1. Enter a wrong code 2. Repeat at least 20 times 3. Check whether attempts are ever blocked | wrong code entered repeatedly | Attempts are limited or the account is temporarily locked | Result : Account is not locked | Fail | High | Security | Wrong OTP attempts are not limited. Logged as D-08.
TC_OTP_007 | OTP | Resend the OTP | The OTP screen is open and no email arrived | 1. Look for a resend option 2. If present, use it and check that a new code arrives | - | A resend option exists and delivers a fresh code | Result : New otp is sent to mail | Pass |  | UX
TC_OTP_008 | OTP | Refresh the page on the OTP screen | The OTP screen is open | 1. Refresh the browser 2. Try to enter the code and submit | browser refresh | The user can still complete verification | Result : The verification is completed | Pass |  | Negative
TC_OTP_009 | OTP | Login before the email is verified | An account was registered but the OTP was never entered | 1. Register a new account 2. Leave the OTP screen without verifying 3. Try to log in with those credentials | unverified account | Login is blocked until the email is verified | Message displayed: The account doesnot exists | Pass |  | Security | Login is blocked as expected, but the message is unclear and should be reviewed separately.
TC_OTP_010 | OTP | Submit a 5-digit OTP | OTP screen is open | 1. Enter a 5-digit code 2. Submit | 12345 | Verification cannot proceed until all 6 digits are entered | The field waits for all 6 digits before allowing verification | Pass |  | BVA (below length)
TC_OTP_011 | OTP | Submit a 7-digit OTP | OTP screen is open | 1. Enter a 7-digit code 2. Submit | 1234567 | The field limits input to 6 digits or rejects a longer code | The field accepts a maximum of 6 digits; a seventh digit cannot be entered | Pass |  | BVA (above length)
TC_OTP_012 | OTP | Enter letters in the OTP field | OTP screen is open | 1. Enter letters in the OTP field 2. Submit | ABCDEF | Letters are blocked or submission is rejected with a numeric-code message | Letters are not accepted; the field accepts numbers only | Pass |  | Negative / EP
TC_OTP_013 | OTP | Verify a valid OTP beginning with zero | A valid code beginning with zero has been issued | 1. Enter the complete code including the leading zero 2. Submit | 0xxxxx | The leading zero is preserved and verification succeeds | Result : Not accept other then numbers | Not Executed |  | BVA / Data | The recorded result does not test whether a leading zero is preserved. Retest with a valid OTP beginning with 0.
TC_OTP_014 | OTP | Use the previous OTP after requesting resend | A second OTP has been requested | 1. Request a new OTP 2. Enter the previous OTP 3. Submit | previous OTP | The previous OTP is invalidated and rejected | Message displayed: Wrong OTP | Pass |  | Negative / Security
TC_OTP_015 | OTP | Request OTP resend repeatedly | OTP screen is open | 1. Select Resend repeatedly 2. Observe whether requests are delayed or limited | multiple resend requests | OTP resend is rate-limited by a visible cooldown period | A new OTP can be requested after a 2-minute cooldown | Pass |  | Security / Negative

## Login
TEST CASES - USER LOGIN (Login screen)
Test Case ID | Module | Test Scenario | Precondition | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Technique | Remarks
TC_LOGIN_001 | Login | Login with valid credentials | A verified account exists and the Login page is open | 1. Enter the registered email 2. Enter the correct password 3. Click Login | joshiaavash111@gmail.com / valid password | Login succeeds and the user reaches the correct account page | Message Displayed : Login Successful | Pass |  | Positive
TC_LOGIN_002 | Login | Submit with Email empty | Login page is open | 1. Leave Email blank 2. Enter a valid password 3. Click Login | email blank / valid password | Login is blocked and a validation message identifies the Email field | Message Displayed : Please Enter Email ID | Pass |  | Negative
TC_LOGIN_003 | Login | Submit with Password empty | Login page is open | 1. Enter a registered email 2. Leave Password blank 3. Click Login | joshiaavash111@gmail.com / password blank | Login is blocked and a validation message identifies the Password field | Message Displayed : Please Enter Password | Pass |  | Negative
TC_LOGIN_004 | Login | Submit with Email and Password empty | Login page is open | 1. Leave both fields blank 2. Click Login | email blank / password blank | Login is blocked and validation messages identify all required fields | Message Displayed : Please Enter Email ID and Password | Pass |  | Negative
TC_LOGIN_005 | Login | Login with an invalid email format | Login page is open | 1. Enter an incorrectly formatted email 2. Enter any password 3. Click Login | joshiaavash111@ / valid password | Login is blocked and an invalid-email message is displayed | Message Displayed : Please Enter valid Email ID | Pass |  | Negative / EP
TC_LOGIN_006 | Login | Login with an unregistered email | Login page is open | 1. Enter an unregistered email 2. Enter a valid-format password 3. Click Login | unregistered.user@gmail.com / valid password | Login is rejected without revealing sensitive account-registration details | Message Displayed : Please Enter valid Email ID | Pass |  | Negative / Security | The generic response avoids confirming whether an account exists, although its wording could be clearer.
TC_LOGIN_007 | Login | Login with an incorrect password | A verified account exists and the Login page is open | 1. Enter the registered email 2. Enter an incorrect password 3. Click Login | joshiaavash111@gmail.com / incorrect password | Login is rejected and the account page does not open | Message Displayed : Please Enter valid Password | Pass |  | Negative
TC_LOGIN_008 | Login | Verify password case sensitivity | A verified account exists and the Login page is open | 1. Enter the registered email 2. Change the letter case of the correct password 3. Click Login | joshiaavash111@gmail.com / password with changed case | Login is rejected because passwords are case-sensitive | Message Displayed : Please Enter valid Password | Pass |  | Negative / EP
TC_LOGIN_009 | Login | Login using uppercase email letters | A verified account exists with joshiaavash111@gmail.com | 1. Enter JOSHIAAVASH111@GMAIL.COM 2. Enter the correct password 3. Click Login | JOSHIAAVASH111@GMAIL.COM / valid password | The email is treated case-insensitively and login succeeds | Message Displayed : Please Enter valid Email ID | Fail | Medium | Positive / EP | The registered email is rejected when entered in uppercase, although email matching should be case-insensitive. Logged as D-09.
TC_LOGIN_010 | Login | Login with spaces around the email | A verified account exists and the Login page is open | 1. Enter spaces before and after the registered email 2. Enter the correct password 3. Click Login | ' joshiaavash111@gmail.com ' / valid password | Spaces are trimmed and login succeeds | Message Displayed : Login Successful | Pass |  | Positive / EP
TC_LOGIN_011 | Login | Login before email verification | An account is registered but its OTP has not been verified | 1. Enter the unverified account email 2. Enter its correct password 3. Click Login | unverified account credentials | Login is blocked until email verification is completed | Message Displayed : Please Enter valid Email ID | Pass |  | Security | Access is blocked as expected, but the message should explain that email verification is required.
TC_LOGIN_012 | Login | Submit repeated incorrect passwords | A verified account exists and the Login page is open | 1. Enter the registered email 2. Submit an incorrect password repeatedly 3. Observe throttling or temporary lock behaviour | 20 repeated incorrect passwords | Repeated attempts are rate-limited or temporarily blocked with clear feedback | Result : Account is not blocked | Fail | High | Security / Negative | Repeated incorrect-password attempts do not trigger throttling or a temporary lock. Logged as D-10.
TC_LOGIN_013 | Login | Enter an SQL-injection-style value | Login page is open | 1. Enter the test string in Email or Password 2. Click Login 3. Observe the response | ' OR '1'='1 | Input is handled safely, login is rejected and no technical error is exposed | Message Displayed : Please Enter valid Email ID | Pass |  | Security
TC_LOGIN_014 | Login | Enter an XSS-style value | Login page is open | 1. Enter the test string in Email 2. Enter any password 3. Click Login 4. Observe the page | <script>alert(1)</script> | The value is treated as text, no script runs and login is rejected | Message Displayed : Please Enter valid Email ID | Pass |  | Security
TC_LOGIN_015 | Login | Double-click the Login button | Valid credentials are entered | 1. Enter valid credentials 2. Double-click Login quickly 3. Observe navigation and requests | joshiaavash111@gmail.com / valid password | Only one login request/session is processed and navigation occurs once | Message Displayed : Login Successful Result : only one login session occurs | Pass |  | Negative / Data

## Defects
DEFECT LOG - AUTH MODULE
Defect ID | Test Case | Summary | Severity | Actual Behaviour | Why It Matters
D-01 | TC_REG_007 | Full Name field accepts digits | Medium | Registration succeeds with the name Aavash123. | Invalid names may be saved and shown on job applications.
D-02 | TC_REG_013 | Mobile numbers beginning with 97 are rejected | Medium | Registration is blocked for the valid Nepali mobile number 9741234567. | Users with valid 97 mobile numbers cannot create an account.
D-03 | TC_REG_018 | Full Name field accepts unsupported symbols | Medium | Registration succeeds with unsupported symbols in the name: aavash@#$. | Invalid symbols may be saved in the user's name.
D-04 | TC_REG_024 | Valid minimum-length password is rejected | Medium | A 6-character password that meets the displayed character rules is rejected. | Users may be unable to register even when their password follows the shown rules.
D-05 | TC_REG_025 | Password without an uppercase letter is accepted | Medium | Registration succeeds with test@123 even though it has no uppercase letter. | Weak passwords can be accepted, reducing account security.
D-06 | TC_REG_028 | Valid non-Gmail email addresses are rejected | Medium | A valid Outlook email is rejected because the address does not end with @gmail.com. | Users with valid Outlook or Yahoo emails cannot register.
D-07 | TC_OTP_006 | No limit on wrong OTP attempts | High | A wrong OTP can be submitted repeatedly without a lock or attempt limit. | Attackers can keep guessing OTPs without restriction.
D-08 | TC_LOGIN_009 | Login rejects uppercase form of a registered email | Medium | The registered Gmail address is rejected when entered in uppercase letters. | A valid user may be unable to log in because of email letter case.
D-09 | TC_LOGIN_012 | No limit on repeated incorrect-password attempts | High | Repeated wrong passwords do not trigger throttling or a temporary lock. | Attackers can keep guessing passwords without restriction.

## Summary
TEST EXECUTION SUMMARY
Metric | Signup | OTP | Login | Total
Total test cases | 28 | 15 | 15 | 58
Pass | 22 | 13 | 13 | 48
Fail | 6 | 1 | 2 | 9
Blocked | 0 | 0 | 0 | 0
Not Executed | 0 | 1 | 0 | 1
Executed so far |  |  |  | 57
Pass rate (of executed) |  |  |  | 84.21%
DEFECTS FOUND
Defect ID | Test Case | Summary | Severity
D-01 | TC_REG_007 | Full Name field accepts digits | Medium
D-02 | TC_REG_013 | Mobile numbers beginning with 97 are rejected | Medium
D-03 | TC_REG_018 | Full Name field accepts unsupported symbols | Medium
D-04 | TC_REG_024 | Valid minimum-length password is rejected | Medium
D-05 | TC_REG_025 | Password without an uppercase letter is accepted | Medium
D-06 | TC_REG_028 | Valid non-Gmail email addresses are rejected | Medium
D-07 | TC_OTP_006 | No limit on wrong OTP attempts | High
D-08 | TC_LOGIN_009 | Login rejects uppercase form of a registered email | Medium
D-09 | TC_LOGIN_012 | No limit on repeated incorrect-password attempts | High
DEFECTS BY SEVERITY
Severity | Count | Defect IDs
High | 2 | D-07, D-09
Medium | 7 | D-01, D-03, D-04, D-05, D-06, D-07, D-09
Total | 9
KEY FINDINGS
High-priority issues: wrong OTP attempts (D-08) and wrong-password attempts (D-10) have no limit. Registration defects are listed first, followed by OTP and Login defects.